## Construction Gantt Chart
Bee-Company
Project: |  | Dashboard
Gantt Chart
Activities |  |  | DURATION (Days)
START DATE | END DATE | DESCRIPTION
2020-10-10 | 2020-10-11 | Project goals and MVP | 1
2020-10-11 | 2020-10-12 | Project planning | 1
2020-10-12 | 2020-10-13 | Information architecture | 1
2020-10-13 | 2020-10-14 | Create mockups | 1
2020-10-14 | 2020-10-15 | Estimating efforts | 1
2020-10-15 | 2020-10-16 | write first report | 1
2020-10-16 | 2020-10-17 | environment setup | 1
2020-10-17 | 2020-10-18 | Setup of backend server | 1
2020-10-18 | 2020-10-19 | Create & development of web routes | 1
2020-10-19 | 2020-10-20 | overview dashboard development | 1
2020-10-20 | 2020-10-21 | finantial dashboard development | 1
2020-10-21 | 2020-10-22 | sales dashboard development | 1
2020-10-22 | 2020-10-23 | procurement dashboard development | 1
2020-10-23 | 2020-10-24 | inventory dashboard development | 1
2020-10-24 | 2020-10-25 | product and client dashboard development | 1
2020-10-25 | 2020-10-26 | final report and last adjustements | 1
Formulas:
END DATE = [START DATE]+DAY(F13)

## Useful Tips
USEFUL TIPS
1 | When enteringactivity start and end dates in columns "C" and "D" use the following date format: DD/MM/YYYY
2 | To change colour of fill and text in cells, use HOME -> FONT tool palette.
3 | To change the start date shown on the gantt chart: Fotmat -> (Current Selection tab) Format Selection -> Axis Options -> Bound: Minimum -> Change value to a number that will be appropriate for your project start date. e.g. 43831 = 1/1/2020 44197 = 1/1/2021 44562 = 1/1/2022 .....

## ©
© TemplateLab.com